## Project Plan
PROJECT | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | TIMELINE
Judul | Medical Check-Up | Aurora Launch | Aurora Launch | Koordinator |  | Wahyuadin | Jordan Lee | TOTAL MODUL | TOTAL TASKS | TOTAL TASKS | TOTAL TASKS | SELESAI | COMPLETE | COMPLETE | COMPLETE | BERJALAN | IN PROGRESS | IN PROGRESS | IN PROGRESS | BELUM MULAI | AT RISK | AT RISK | AT RISK
Aplikasi | Web Base | Northstar Labs | Northstar Labs | Mulai |  | 2026-10-07 | 2026-07-06 | 6 |  |  |  | 3 |  |  |  | 3 |  |  |  | 5
MODUL | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | DATE SCHEDULE PLANT | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW
Modul | Item | Approve By | Status belajar | Catatan | Mulai | Selesai | Hari | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-11-01
1. Authentifikasi | Login, hak akses, dan dashboard | Pak Agung | Selesai | - | 2026-10-07 | 2026-10-08 | 2 | bar: 2026-10-07 to 2026-10-08
2. Master | Data perusahaan, dokter, jadwal, dan paket MCU | Pak Agung | Selesai | - | 2026-10-09 | 2026-10-09 | 1 | bar: 2026-10-09
3. Pendaftaran | Data pasien, foto, dan checkpoint QR | Pak Agung | Selesai |  | 2026-10-09 | 2026-10-09 | 1 | bar: 2026-10-09
4. Pemeriksaan | Riwayat kesehatan, fisik, laboratorium, dan penunjang | - | Berjalan |  | 2026-10-09 | 2026-10-10 | 2 | bar: 2026-10-09 to 2026-10-10
5. Hasil MCU | Kesimpulan, finalisasi, dan revisi hasil | - | Berjalan |  | 2026-10-09 | 2026-10-10 | 2 | bar: 2026-10-09 to 2026-10-10
6. Pelaporan | Laporan, riwayat versi, penutupan, dan audit | - | Berjalan |  | 2026-10-09 | 2026-10-10 | 2 | bar: 2026-10-09 to 2026-10-10
7. Role HRD | Penyusunan Dashboard dan rekapitulasi peserta per masing masing perusahaan | - | Belum mulai |  | 2026-10-10 | 2026-10-10 | 1 | bar: 2026-10-10
8. Report HRD | Laporan Rekap Resume, dan Rekap hasil | - | Belum mulai |  | 2026-10-11 | 2026-10-11 | 1 | bar: 2026-10-11
9. Role Petugas | Implementasi QR peserta dan testing | - | Belum mulai |  | 2026-10-12 | 2026-10-13 | 2 | bar: 2026-10-12 to 2026-10-13
10. Sandbox Mode | Review dan Trial dan Error | - | Belum mulai |  | 2026-10-12 | 2026-10-14 | 3 | bar: 2026-10-12 to 2026-10-14
11. Production | Upload ke server Production | - | Belum mulai |  | 2026-10-14 | 2026-10-15 | 2 | bar: 2026-10-14 to 2026-10-15